## Slide 1
RIVERSIDE
Q1 FY26 Retro
Marketing Operations
Feb 1, 2026 to Apr 30, 2026
Hanan Amos · Head of Marketing Operations

## Slide 2
The Team
Marketing Ops · Q1 FY26 Retro
Three direct reports, plus four contracted contributors who delivered alongside us in Q1.
Hanan Amos
Head of Marketing Operations
MOps lead, attribution strategy, AI tooling rollout, HubSpot architecture.
Jonathan Galili
Marketing Operations
Engineering side of MOps. Data integrations, HubSpot infrastructure, attribution pipelines, reporting.
Yuval Tsabar
Marketing Website
riverside.com pages, A/B tests, accessibility, localization. Owns the Website Development board and #website-dev.
Contributing contractors:
Davor (39 shipped) · Milutin (20) · Raphael Landau (13) · Igor Suprun (5)
Riverside Growth · Marketing Operations
2 / 18

## Slide 3
TL;DR
Marketing Ops · Q1 FY26 Retro
Marketing Ops shipped 245 of 339 planned items in Q1, a 72% completion rate across two monday boards.
Output was led by Yuval (98 shipped), Hanan (68), Jonathan (57), with significant volume from contracted contributors.
The headline insight: 85% of all Q1 items were unplanned. The team is operating in heavily reactive mode.
Closing the gap between 43 planned and 339 actual is the single most important Q2 question.
94 items carry over into Q2, including 7 P0 / Urgent items.
Riverside Growth · Marketing Operations
3 / 18

## Slide 4
By the Numbers
Marketing Ops · Q1 FY26 Retro
339
items planned in Q1 (across both boards)
245
shipped (72%)
87
carrying into Q2
MOps Tasks board
193 items · 128 shipped (66%)
Website Dev board
146 items · 117 shipped (80%)
Volume peak
Feb 130 · Mar 121 · Apr 54
Sources: monday.com Marketing Operations Tasks board (6257866754) and Website Development board (18397093471), items with Q1 due dates.
Riverside Growth · Marketing Operations
4 / 18

## Slide 5
Output by Team Member
Marketing Ops · Q1 FY26 Retro
Yuval Tsabar
98
Hanan Amos
68
Jonathan Galili
57
Davor
39
Milutin
20
Raphael Landau
13
Igor Suprun
5
Direct reports
Contracted contributors
Yuval led individual output. The function delivered through a 3-person core plus 4 contracted contributors.
Riverside Growth · Marketing Operations
5 / 18

## Slide 6
Planned vs Unplanned (Headline Insight)
Marketing Ops · Q1 FY26 Retro
85% of all Q1 work was unplanned. The team is operating in a heavily reactive mode.
43
PLANNED
13% · on the books before Q1
or tagged Planned on Web Dev board
287
UNPLANNED
85% · added in-flight during Q1
Per board:
MOps Tasks board
Proxy: created before Feb 1
24 planned
169 unplanned (88%)
Website Dev board
Native field: Planned?
19 planned
118 unplanned (81%)
Closing this gap is the single most important Q2 question. Aim to shift toward 30/70 by end of Q2.
Riverside Growth · Marketing Operations
6 / 18

## Slide 7
MOps Output by Type
Marketing Ops · Q1 FY26 Retro
Marketing Operations Tasks board only. Website Dev board does not categorize by type.
Reporting / Dashboard
23
Biz Process
22
HubSpot
19
Data Integration
18
Website Related
16
Issue / Bugs
11
Messaging
9
Website A/B Test
4
Email Blast
2
Attribution
1
Reporting and HubSpot together accounted for a third of MOps Tasks output. Web Dev added 117 more shipped items on top: page launches, A/B tests, localization, accessibility, security fixes.
Riverside Growth · Marketing Operations
7 / 18

## Slide 8
Wins
Riverside Growth · Marketing Operations
8 / 18

## Slide 9
7 Wins Worth Celebrating
Marketing Ops · Q1 FY26 Retro
01
Self-Attribution Channel infra + weekly Slack report
New HubSpot property auto-tags every Enterprise form fill. Weekly digest in #growth-marketing-leaders. (Hanan)
02
AI tooling rollout for the team
Mixpanel and Omni added to Claude as MCP connectors. Brand skill, deck-builder skill. (Hanan)
03
HubSpot lifecycle and PLG framework
PLG Lifecycle, framework rebuild, French welcome drip, ChiliPiper fix, Win-back segmentation. (Hanan, Jonathan)
04
Reporting depth
Mixpanel A/B revamp, PPC dashboard template, Subscription cancellations, Newsletter, Organic traffic. (Jonathan, Hanan)
05
Localization expansion
French marketing pages launched, DE locale fixed, German pricing page recovered, Israel pages added. (Yuval, Raphael)
06
Accessibility audit implementation
Header, footer, product pages remediated for AA. Dedicated #website-accessibility channel. (Yuval, Raphael)
07
Operational reliability across the website
PPC 404 alerts, Cloudfront triage, /plans-/pricing redirect, /de cleanups, security fix, navbar bug crush. (Yuval, Jonathan)
Riverside Growth · Marketing Operations
9 / 18

## Slide 10
Misses and Stuck Work
Riverside Growth · Marketing Operations
10 / 18

## Slide 11
P0 / Urgent Carryovers into Q2
Marketing Ops · Q1 FY26 Retro
Seven items entering Q2 with top-priority. Five are infrastructure or data-flow, two are urgent website assets.
Status
Type
Owner
Item
Source
Working on it
Website
Jonathan
Cloudfront caching causing intermittent 404s
MOps · P0
Working on it
Data Int.
Jonathan
iOS revenue data not displaying in AppsFlyer Analytics
MOps · P0
Working on it
Data Int.
Jonathan
Multi-account feature and HubSpot data flow
MOps · P0
Test is Open
A/B Test
Jonathan
Home LP A/B test
MOps · P0
New
Biz Process
Hanan
Budget report process with Erika
MOps · P0
New
Web Asset
Yuval
Static Assets - Love & Labor
Web · Urgent
New
Web Asset
Yuval
Love and Labor: Birth certificate LP
Web · Urgent
Riverside Growth · Marketing Operations
11 / 18

## Slide 12
P1 Carryovers Worth Flagging
Marketing Ops · Q1 FY26 Retro
Attribution debt
Fix UTM attribution (past UTMs always showing). Mobile app events for FB apps and separate funnel events. Daily event log to correlate activity with metric drops/increases.
HubSpot investigation pileup
Multiple 'Investigate HubSpot contact...' tickets opened in April never moved past New. Pattern: investigation work gets logged but not scheduled.
SEO debt
'SEO debts: provide plan and ETA for no-index and robots.txt fixes' and 'Find independent solution for robo.txt management, remove dev dependency'. Both still New.
Website backlog
Page URL cache (P1, no movement). Anomaly detection and on-call protocol for Website (P1, dropped). Replace internal links to parametrized URLs (Working on it).
Riverside Growth · Marketing Operations
12 / 18

## Slide 13
Themes That Drove the Quarter
Marketing Ops · Q1 FY26 Retro
01
Performance pressure was the dominant context
Feb closed at 78% of target. Signups down 14%, trials down 8%. Nir publicly called for new sources and CVR experiments. This shaped priority more than any planning doc.
02
AI adoption became a strategic Hanan-led project
The team explicitly debated Claude vs GPT in early March. Hanan led the answer. Claude MCP rollouts for Mixpanel and Omni were felt across the team.
03
External event in early March slowed everyone down
March 9 to 10 messages line up with the March creation peak (121) and explain April's drop to 54. Q1 was not a smooth quarter.
04
Website ops is its own throughput, not overflow
Yuval's 98 shipped items and the Web Dev board's 117 closes prove this. Should be planned for explicitly, not treated as background noise.
Riverside Growth · Marketing Operations
13 / 18

## Slide 14
Process Patterns to Fix
Marketing Ops · Q1 FY26 Retro
85% reactive, 15% planned
Of 339 Q1 items, only 43 were planned. This is a structural feature of the function. Q2 planning will not bend the curve unless intake changes.
MOps board fields are decorative
173 of 193 items stuck in Stage = Requirements. 189 of 193 tagged 'Increase Engagement' as Primary Goal. Both fields add zero signal.
Priority inflation on MOps board
72 P1s plus 17 P0s out of 193: ~46% of work is P1-or-higher. Nir flagged this in March. The label has lost its tradeoff power.
Web Dev does Planned? right
Yuval is correctly tagging Planned vs Unplanned items. The data is reliable. Bring this practice to the MOps Tasks board.
Riverside Growth · Marketing Operations
14 / 18

## Slide 15
Lessons for Q2
Marketing Ops · Q1 FY26 Retro
1
Treat planned/unplanned as a real metric.
Track it weekly. Aim to shift from 13/87 toward 30/70 by end of Q2. Either more planned work entering, or fewer unplanned accepted.
2
Adopt Web Dev's Planned? field on MOps Tasks.
Yuval already does this correctly. Bring the practice to the MOps board so future retros can use real data, not a created-date proxy.
3
Re-baseline priority on MOps board.
No more than 5 active P0s at once. No more than 25% of open work tagged P1. Forces real tradeoffs.
4
Triage New items weekly.
30 minutes Mondays for #mops-priority-room and the Tasks board. Catches the April investigation pileup pattern.
5
Budget for website ops explicitly.
98 items shipped by Yuval is not overflow. Plan capacity for it the way we plan for HubSpot or attribution.
6
Capture the AI tooling work in this repo.
Brand skill, MCP rollouts, deck-builder skill are load-bearing and live mostly in Hanan's head.
Riverside Growth · Marketing Operations
15 / 18

## Slide 16
Q2 Implications
Marketing Ops · Q1 FY26 Retro
CARRY
Must finish
• 5 MOps P0s (Cloudfront, iOS AppsFlyer, Multi-account HubSpot, Home LP test, Budget report)
• 2 Web Dev Urgents (Love & Labor static assets, birth certificate LP)
• Open A/B tests (Descript vs CoCo, Home LP). Decide ship or kill in Week 1.
KILL or DEFER
Suggested
• 'Clarify Teamblind LP in Claude' (P1, March 17, no movement). Not a P1.
• April HubSpot investigation pileup. Triage Week 1: commit or close.
• Old Web Dev Stuck items from Feb (webinar image, /community code cleanup).
SCALE
Worked, do more
• Self-Attribution weekly report. Add SLG funnel UTM and paid attribution.
• AI tooling. HubSpot MCP playbook, 'campaign report in 60s', brand-asset workflows.
• Yuval's planning discipline. Bring Planned? field to MOps Tasks board.
• Localization. FR live, DE recovered. More locales likely in Q2.
Riverside Growth · Marketing Operations
16 / 18

## Slide 17
Open Questions for the Q2 Plan
Marketing Ops · Q1 FY26 Retro
?
Are we accepting the 85% reactive rate, or actively trying to bend it? With what mechanism?
?
Who triages new requests entering both boards? Hanan as filter, or each owner filters their own?
?
What capacity reservation for unplanned in Q2 (e.g. 50% of bandwidth) vs planned initiatives?
?
Should we add a Type / Area-of-impact column on the Web Dev board so future retros can categorize its output?
Riverside Growth · Marketing Operations
17 / 18

## Slide 18
Thank you.
Onwards to Q2.
Hanan · Jonathan · Yuval
Marketing Operations · Riverside Growth